## Summary
Instant Retail Co. — Tier 3-4 Strategy Work Plan
Key Question: | How to achieve EBIT turnaround in Tier 3-4 cities within 3 years?
Date: | 2026-04-30
Analysis Deadline: | 2026-05-03 (EOB)
Submission Deadline: | 2026-05-06
Workstream Overview
Workstream | Focus Area | # Analyses | Effort | Key Dependency
WS-A: City Portfolio Decisions | fa-city | 5 | 40% | None (data ready)
WS-B: Competitive Constraint Boundaries | fa-competition | 3 | 30% | Web research (subagent)
WS-C: Subsidy Precision Opportunity | fa-subsidy | 3 | 30% | WS-B scenarios feed into C3
Critical Path Note: | WS-A4 (EBIT Scenario Model) and WS-B3 (Competitive Scenarios) are gating analyses. WS-C3 depends on WS-B3.

## Detailed Analysis Plan
ID | Workstream | Analysis Name | Question to Answer | Approach | Data Needed | Data Source | Data Status | Output Format | Hypothesis | Priority | Dependencies | Status
AX-A1 | WS-A | 10-City Comparative Financial Analysis | Which cities have best/worst unit economics and why? | Cross-sectional comparison: AOV, cost, subsidy, cost/AOV, user%, category mix | 10-city dataset | 01-problem-definition.md | Available | City ranking table + 2x2 matrix | C3/C7/C8 best; C9/C10/C4 worst | P1 | None | Not Started
AX-A2 | WS-A | Three Hemorrhage-Cities Profit Path Analysis | How does each of 3 priority cities (Quanzhou/Huizhou/Weihai) achieve EBIT+? Are paths different? | Unit economics decomposition per city; EBIT driver attribution | 10-city dataset | 01-problem-definition.md | Available | 3-city comparison table; driver attribution | Quanzhou=large super; Huizhou=scale; Weihai=AOV — 3 paths = 3 playbooks | P1 | AX-A1 (parallel) | Not Started
AX-A3 | WS-A | Selective Contraction Cost-Benefit Analysis | What savings from exiting or shrinking C9/C10/C4/C5? | Estimate annual loss; model savings from partial/full exit (fixed cost relief + subsidy elimination) | Annual loss estimates | 01-problem-definition.md | Available (estimated) | Savings range table; exit sequencing | Full exit of 2 worst = ~3,000万; partial exit of 4 = ~2,000万 | P1 | AX-A1 (parallel) | Not Started
AX-A4 | WS-A | 3+3+4 City Grouping EBIT Scenario Model | What does 3-year EBIT path look like under 3 scenarios? | 3-scenario financial model; Year 1: 3 cities EBIT+; Year 2: +3 cities; Year 3: portfolio EBIT+ | AX-A1/02/03 outputs | 01-problem-definition.md | Available | 3-year EBIT bridge per scenario; breakeven timing | Even conservative: 3-city focus achieves EBIT+ by Year 2 | P1 | AX-A1, A2, A3 (gating) | Not Started
AX-A5 | WS-A | Weihai Model Replicability Assessment | Can Weihai formula be replicated? What are preconditions? | Compare Weihai driver profile vs. other cities; rank by Weihai-fit; AOV uplift pathway | 10-city dataset | 01-problem-definition.md | Available | Cities ranked by Weihai-fit; AOV uplift pathway | Partially replicable in C7/C1; not in C9/C10 short-term | P2 | AX-A1, A2 (parallel) | Not Started
AX-B1 | WS-B | Meituan Public Financials Research | What does Meituan spend on subsidies and R&D per order in Tier 3-4? | Search Meituan 2024 annual report; investor presentations; analyst call transcripts; 四五线城市 subsidy data | Meituan IR, Bloomberg, Goldman/DB reports | Public financials / analyst reports | Need (web search) | Key findings memo: subsidy floor; Tier 3-4 strategy remarks | National data only; no city-level; medium confidence | P1 | None | Not Started
AX-B2 | WS-B | JD.com Public Financials Research | What is JD.com instant retail strategy in lower-tier cities? | Search JD.com 2024 annual report; JD到家 investor materials; Analysys market share | JD IR; Analysys; iiMedia | Public financials | Need (web search) | Key findings memo: competitive intensity; JD到家 differentiation | Medium confidence | P1 | AX-B1 (parallel) | Not Started
AX-B3 | WS-B | Competitive Intensity Scenario Analysis | How do competitive scenarios constrain subsidy reduction options? | Synthesize B1+B2 into 3 scenarios (high/med/low); subsidy floor per scenario; response options | AX-B1, B2 outputs | B1+B2 research | Pending B1/B2 | 3x3 scenario matrix; subsidy floor per scenario | Even high-competition: some subsidy reduction feasible if targeting low-value users only | P1 | AX-B1, B2 (gating) | Not Started
AX-C1 | WS-C | Subsidy Efficiency Diagnostic | How is 4.2元/order subsidy distributed across city and user quality tiers? | Cross-city comparison: subsidy/order vs. high-value user%; worst efficiency cities | Subsidy and user% per city | 01-problem-definition.md | Available | Subsidy efficiency ranking table; waste rate proxy | C10 has highest subsidy + lowest high-value% = worst efficiency | P1 | None | Not Started
AX-C2 | WS-C | High-Value User Improvement Potential Analysis | What does Weihai (26%) vs. Ganzhou (15%) gap tell us about improvement potential? | Compare Weihai vs. Ganzhou characteristics; identify structural drivers of 11pp gap | City and user characteristics; category mix; large super% | 01-problem-definition.md | Partial (断面; no longitudinal) | Gap decomposition; qualitative improvement pathway | Gap partly due to category mix + large super depth — both actionable within 12 months | P1 | AX-A1 (parallel) | Not Started
AX-C3 | WS-C | Subsidy Reallocation Scenario Analysis | Financial impact of reallocating subsidy from low-value to high-value users? | 3 scenarios (conservative/base/optimistic) for 12-month reallocation; subsidy savings × high-value% trajectory | AX-C1, C2 outputs; AX-B3 competitive ceiling | AX-C1, C2, B3 | Pending (partial inputs) | Subsidy savings range per scenario; high-value% trajectory | Conservative: -10% low-value; Base: -20% + retention incentive; Optimistic: full reallocation | P1 | AX-C1, C2, AX-B3 (gating) | Not Started

## Data Inventory
Data Item | Source | Status | Format | Notes | Workaround if Unavailable
10-city AOV, order volume, costs | 01-problem-definition.md | Have | Embedded in doc | Primary data source | N/A
City-level loss estimates | 01-problem-definition.md | Have (estimated) | Embedded in doc | Estimated by CSO, not actuals | Use as proxies; flag as estimated
High-value user % by city | 01-problem-definition.md | Have | Embedded in doc | 15-26% range | N/A
Large supermarket % by city | 01-problem-definition.md | Have | Embedded in doc | 12-23% range | N/A
Category mix by city | 01-problem-definition.md | Have | Embedded in doc | 生鲜/餐饮/到家快消 % | N/A
City open year, market share | 01-problem-definition.md | Have | Embedded in doc | 2018-2022 range | N/A
Monthly/quarterly trends | None | Unavailable | N/A | No monthly data provided | Do not estimate; use断面 snapshots only
User retention/repurchase curves | None | Unavailable | N/A | Known gap — no cohort data | Use scenario ranges (low/base/high); do not fabricate
Fixed cost breakdown | None | Unavailable | N/A | Fixed/变动 split not provided | Use estimated annual loss as proxy for fixed cost burden
Meituan Tier 3-4 subsidy data | Public financials / analyst reports | Need | Annual report / analyst report | No city-level disclosure; national data only | Use as ceiling; acknowledge uncertainty
JD.com instant retail data | Public financials | Need | Annual report | JD到家 regional data not disclosed | Proxy from industry reports
Competitive intensity in target cities | Industry reports | Need | Research report | Analysys易观 may have market share data | Qualitative scenario framing