## Summary
Project Name | Key Question | Date | Timeline
Instant Retail Co. O2O Strategy | How can Instant Retail Co. turn its currently unprofitable Tier-3 and Tier-4 operations into a sustainable, profit-contributing engine? | April 30, 2026 | ASAP
Workstream Name | # Analyses | Effort | Milestone
WS1: City Portfolio Logic & Prioritization | 3 | High | City Scoring Matrix & Selection
WS2: Fulfillment & Operating Model Pivot | 2 | High | Business Model Comparison
WS3: Subsidy Optimization & 3-Year Break-Even | 3 | Medium | Unit Economics Break-Even Model

## Detailed Analysis Plan
ID | Workstream | Analysis Name | Question to Answer | Data Needed | Data Source | Output Format | Priority | Status
WS1-A1 | 1. City Portfolio | Profitability Diagnostic | What are the root causes of per-order losses in each city? | AOV, Fulfillment, Subsidy per order | Internal Excel | Waterfall Chart | P1 | Not Started
WS1-A2 | 1. City Portfolio | City Scoring Model | Which cities should we Invest, Optimize, or Exit? | Macro data, MAU, O2O share, growth | Internal Excel | 2x2 Matrix & Table | P1 | Not Started
WS1-A3 | 1. City Portfolio | Competitor Heatmap Proxy | Where is competitor intensity lowest? | External reports on Meituan/JD presence | Public Reports | Map / Table | P2 | Not Started
WS2-A1 | 2. Operating Model | Fulfillment Cost Density Analysis | What is the gap between current order density and viable fulfillment costs? | Pop density, Order vol, Fulfillment cost | Internal Excel | Scatter Plot | P1 | Not Started
WS2-A2 | 2. Operating Model | Business Model Scenario Comparison | Dark Store vs Flash Warehouse vs Marketplace - which breakevens fastest? | Fulfillment cost benchmarks per model | Internal Excel & Benchmarks | Decision Matrix & P&L | P1 | Not Started
WS3-A1 | 3. Subsidy & Break-Even | Subsidy vs. High-Value User Correlation | Are subsidies driving sticky users or just opportunistic volume? | High-value user %, Subsidy per order | Internal Excel | Correlation Chart | P1 | Not Started
WS3-A2 | 3. Subsidy & Break-Even | Subsidy Tapering Sensitivity | What happens to volume/P&L if we cut subsidies by 20-30%? | Price elasticity estimates | Assumptions | Sensitivity Table | P2 | Not Started
WS3-A3 | 3. Subsidy & Break-Even | 3-Year Bottom-Up Break-Even Path | When will priority cities flip to profitability? | Projected AOV, orders, costs | Model Output | Timeline & Waterfall | P1 | Not Started

## Data Inventory
Data Item | Source | Status | Notes
City-level P&L and Unit Economics (AOV, Fulfillment, Subsidy) | Internal Excel | Available | Complete for all 10 cities
City Scale & User Base (Orders, MAU, High-Value %) | Internal Excel | Available | Complete for all 10 cities
Market Position (Market Share, YoY Growth) | Internal Excel | Available | Complete
Macro Context (Population, GDP, Income) | Internal Excel | Available | Complete
Competitor Presence (Meituan, Alibaba, JD) | External Search | Needed | Need proxies if direct data unavailable
Fulfillment Model Benchmarks (Dark Store vs Flash vs Marketplace) | External/Assumptions | Needed | Critical for WS2